Equity Tracker

Quarterly Release Schedule — 2026

Document Owner: Product Management
Version: 1.0
Last Updated: September 15, 2026
Status: Approved

# 1. Overview

This document defines the 2026 quarterly release schedule for the Equity Tracker, the platform used to monitor portfolios, watchlists, and market data for equity research. Each quarter delivers one major release, followed by a stabilization patch. Dates are targets and may shift by up to two weeks based on QA results and market-data vendor dependencies.

Release cadence: one major release per quarter (weeks 10–11 of the quarter), with a patch release approximately three weeks later. Hotfixes are released as needed outside this cadence.

# 2. Release Schedule by Quarter

## Q1 2026 — Foundation & Data Quality

Theme: harden the core platform and improve the reliability of market data ingestion.

| Release | Version | Target Date | Key Deliverables | Status |
| --- | --- | --- | --- | --- |
| R1.0 | v2.4.0 | Mar 12, 2026 | Real-time price feed upgrade; ticker deduplication; portfolio import from CSV/Excel; audit logging | Released |
| R1.1 | v2.4.1 | Apr 2, 2026 | Stabilization patch: feed reconnection fixes, import edge cases, performance tuning | Released |

## Q2 2026 — Analytics & Screening

Theme: expand analytical tooling for research workflows.

| Release | Version | Target Date | Key Deliverables | Status |
| --- | --- | --- | --- | --- |
| R2.0 | v2.5.0 | Jun 11, 2026 | Custom screeners; factor exposure dashboard; earnings calendar integration; export to PDF | Released |
| R2.1 | v2.5.1 | Jul 2, 2026 | Stabilization patch: screener query optimizer, dashboard rendering fixes | Released |

## Q3 2026 — Alerts & Collaboration

Theme: keep analysts informed and enable shared research.

| Release | Version | Target Date | Key Deliverables | Status |
| --- | --- | --- | --- | --- |
| R3.0 | v2.6.0 | Sep 10, 2026 | Price and volume alerts (email/Slack); shared watchlists; research note attachments; role-based access control | Released |
| R3.1 | v2.6.1 | Oct 1, 2026 | Stabilization patch: alert delivery retries, permissions edge cases | In Progress |

## Q4 2026 — Intelligence & Scale

Theme: automated insights and platform scalability.

| Release | Version | Target Date | Key Deliverables | Status |
| --- | --- | --- | --- | --- |
| R4.0 | v2.7.0 | Dec 10, 2026 | AI-assisted research summaries; anomaly detection on holdings; API v2 for external integrations; dark mode | Planned |
| R4.1 | v2.7.1 | Dec 22, 2026 | Stabilization patch: year-end close support, API hardening | Planned |

# 3. Key Milestones

| Date | Milestone |
| --- | --- |
| Feb 20, 2026 | Q1 feature freeze and start of regression testing |
| May 22, 2026 | Q2 feature freeze; screener beta opens to pilot users |
| Aug 21, 2026 | Q3 feature freeze; alerts load test at 10x volume |
| Nov 20, 2026 | Q4 feature freeze; AI summary accuracy review |
| Dec 31, 2026 | 2027 roadmap finalized and published |

# 4. Release Process

Feature freeze occurs three weeks before each major release date; only bug fixes are merged after freeze.

Release candidates are deployed to staging for a two-week QA and UAT cycle, including market-data replay testing.

Go/no-go review is held two business days before the target date with Product, Engineering, and Research stakeholders.

Production deployments occur outside U.S. market hours (after 5:00 PM ET), with a rollback plan validated in staging.

A stabilization patch is scheduled roughly three weeks after each major release to address issues found in production.

# 5. Revision History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | Sep 15, 2026 | Product Management | Initial approved schedule |